## Issues
ID | Area / Module | Issue Summary | Steps to Reproduce | Expected | Actual | Severity | Status | Phase / Related | Owner | Date Found | Date Resolved | Notes
SC-001 | Deployment / clasp | Phase 11C External_Links flip not live | Validate shadow parity, then run enableClaimsServiceExternalLinks() in dashboard editor | Claims Service is primary External_Links writer | USE_CLAIMS_SERVICE_EXTERNAL_LINKS still false (shadow) | High | Fixed - Needs Deploy | 11C | Julia |  |  | Instant rollback: set flag back to false
SC-002 | Deployment / clasp | Phase11C_TemporaryHelpers not visible in Apps Script editor | clasp push automation-dashboard, or paste file manually | Helper appears in editor file list | File only exists locally, not pushed | Medium | Fixed - Needs Deploy | 11C | Julia
SC-003 | Automation Dashboard | Phase 11D internal-runner dispatch not deployed | clasp push automation-dashboard + redeploy web app | Grid intake retries run in-process | Grid still calls standalone web app | High | Fixed - Needs Deploy | 11D | Julia |  |  | Flag USE_INTERNAL_INTAKE_MODULE default true
SC-004 | EOJ App | New EOJ_Log columns not created | Run repairEOJLogColumns() once in eoj-app editor after push | Extension_Poles_* and Add_To_Tomorrow_Calendar columns exist | Fields captured only in Raw_JSON | Medium | Fixed - Needs Deploy | EOJ detour | Julia |  |  | Non-destructive; adds missing columns only
SC-005 | EOJ App | EOJ visibility changes not deployed | clasp push eoj-app + eoj-processing-engine, redeploy eoj-app web app | Extension Poles, calendar Q, history expand, full Chat live | Not visible in app yet | High | Fixed - Needs Deploy | EOJ detour | Julia |  |  | Use /dev URL to verify
SC-006 | EOJ App | micaUpdated read by element id returns blank | Submit EOJ with Mitigate Yes/No; check MICA_Updated column | MICA_Updated populated | Column may be blank (valueOf reads radio group by id) | Medium | New | Pre-existing | Julia |  |  | Left untouched in EOJ detour - separate fix if wanted
SC-007 | Queue Health | Intake Workspace cold-load latency (~13-30s) | Load Intake Workspace after cache expiry | Fast load | Slow first load; reload mid-load prevents cache populating | Medium | In Progress | 11B/11C | Julia |  |  | Cache-warm trigger implemented, not installed
SC-008 | Automation Dashboard | Cache-warm trigger not installed | Run installIntakeWorkspaceCacheWarmTrigger() after deploy | Cache stays warm business hours | Not scheduled | Low | Fixed - Needs Deploy | 11C | Julia |  |  | Every 5 min, Mon-Fri 6a-7p
SC-009 | Script Properties | Todoist API token shared in plaintext | Generate new token, re-run setTodoistApiTokenForPhase11B('new') | Rotated token | Old token still in use | Low | New | 11B | Julia |  |  | Security hygiene
SC-010 | Automation Dashboard | Temp helper files pending deletion | Confirm properties/flip, then rm + push | Temp files removed | 3 temp files present | Low | New | 11E | Julia |  |  | Phase11BSetup, Phase11BDiag, Phase11C_TemporaryHelpers
SC-011 | Deployment / clasp | Web app pinned-deployment gotcha | After push, redeploy (Manage deployments) or use /dev URL | New code served | Push alone serves old pinned version | High | New | All | Julia |  |  | Tell-tale: workspace loading line text
SC-012 | Deployment / clasp | Phases 11A-11D + EOJ uncommitted in git | Clear stale .git/index.lock, git add scoped files, commit | Clean commit boundary | Working tree has large uncommitted pile; stale index.lock | Medium | New | All | Julia |  |  | Commit before further work
SC-013 | Retry Actions | Standalone scheduled retry triggers still live | Inventory triggers on standalone project | Single owner of scheduled retries | Standalone triggers retained (by design) | Low | New | 11E | Julia |  |  | Retirement deferred to 11E to avoid duplicates

## Lists (hidden)
Intake Workspace | Blocker | New
Intake Pipeline (Run Intake) | High | Investigating
Retry Actions | Medium | In Progress
Queue Health | Low | Blocked
Diagnostics |  | Fixed - Needs Deploy
Pending Folder Inspection |  | Verified
EOJ App |  | Won't Fix
EOJ Processing Engine
Google Chat Notifier
Claims Service
External_Links
Automation Dashboard
Todoist
Calendar
Deployment / clasp
Script Properties
Other